**courtpicker release 1.0**

hours est real

reservation

admin reservation

user selection at admin-view (calculated price can change) 2 1,5

reserve with customer-create option (enter email address) 4 1

extended/new service 1 4,5

reservation category

price calculation

single 8 10

abo

abo-reservation

figure out available abo rates and show them in abo tab if available

own service for abo reservations

views

week-view

capacity indicator (0-green,1/3-yellow,2/3-orange,3/3-red) 0,5 2

with day-selection (maybe completely new view?) 2 0,5

day-view with court selection 3 6

user management

user registration + activation 4 5

finalize “password forgotten” 2 2,5

**configurator**

design

finalise design preview feature 8 10

additional new design elements 2 4,75

registration step after configurator 4 4,5

price calculation after configuration 2 1,5

include numerated header at top of steps 2 2

**admin area**

admin area switch / design 2 2

reservation search (diverse search options) 10 9

reservation actions

mark payed (different payment options) - price must also be adjustable here 4 3,75

cancel (no edit necessary) 1 2,5

manage user groups 8 5,5

manage payment options 4 1,5

manage reservation categories

integrate all configuration steps 4 1

manage permissions 2 1,5

**customer area**

edit customerdata 2 3

my reservations 4 3

cancel my reservations 1 1

**general**

secure api + login 30

design fixes 10 4,5

**other**

setup project on github 7

**OVERALL LEFT HOURS: 105; average 10 h/week 🡪 10,5 weeks 🡪 estimated release: 01.06.14**